## Key Questions
Answer these questions, before filling in the action plan. This will help you identify actions you could take to improve compliance. This list is not exhaustive, and not every question will apply to you. You should take a proportionate approach based on the needs and resources of your individual authority. In general, you should consider: the points in which delay occurs over the lifetime of a request, whether your established request handling process needs to change, and shortfalls in resource and whether anything can be done about them.
Procedural | Who handles requests? | Central FOI team of 2.5 FTE Officers, 0.5 Admin Support and 1 Team Manager. Assistance of approximately 30 FOI contacts throughout the wider organisation.
| How many requests do they work on at a time? | Central team handles between 35 - 45 new cases per week.
| Do they have to prioritise other tasks over handling requests? | FOI responses are the priority within the central team, in the wider organisation Heads of Services and Directors may have to prioritise their BAU. However, handling the back-log is now a priority and discussed at weekly directorate management meetings.
| Do you have sufficient staff to handle requests? | No, however additional staff resource agreed and employment process is currently in motion.
| Do you have an established method for handling requests? | Yes, robust process in place - however the escalation and press sign off process is being reviewed.
| Does it take a long time to consider whether to withhold information? Why? | Officers are given 5 working days to come back to the Central FOI Team before they are chased. By this point it should be known if we need to withhold the information. Additionally, we look at balancing the public interest tests when considering exemptions.
| Do you manage requesters' expectations around timescales, to reduce requests for updates which take staff away from handling information requests? | Yes, on receipt of the request the team might go straight back to the requestor. Additionally, after 5 working days the Central FOI Team are expected to go back to the requestor if Officers inform them that the request cannot be processed within timescales.
| Do you ever extend the time allowed to respond to a request (where that's appropriate, according to the legislation)? | Yes, there is an on-hold-process where clarity is requested, and where we apply the public interest test the process is extended up to the allowed 20 days.
| Do you frequently need to consult third parties about the disclosure of information? Does that cause delays? | Yes, in circumstances as required, for commercial reasons for example. However, we do try to keep this to a minimum. If we don't hear from them within time would usually release the requested information.
| Do your request handlers regularly discuss the requests they’re working on, to share knowledge and best practice? | Yes, within the FOI Central Team at our twice weekly meetings and with the Legal Team as required. Whilst there is a back-log, we are also discussing requests with DMTs on a weekly basis.
| When you issue a response to an information request, do you receive a lot of secondary correspondence asking for clarification? | Whilst requestors do come back with questions, FOI Internal Reviews have declined in recent months; which suggests the quality of our responses has improved.
| Is there a specific type of request that regularly causes you problems? | Not specific requests but those that cover multiple services, which can cause delays and problems collating an individual Officer for the full response. We have reviewed this process recently and identified Directors to coordinate multi-service responses.
| Have you identified any other procedural issues which are slowing you down? | Director approval process and Press sign-off was not fully defined, so could at times could slow the process down. We have recently reviewed this process and allowed 5 working days within the FOI timeframes for this.
Technical | Do you have a dedicated case management system for handling information requests? | Yes, Infreemation.
| How promptly are requests ready to be worked on after they are received by you? | When responses from the wider-organisation are received the Central FOI Team will work on responses straight away and aim to send them out by close of business.
| Does your system make it easy to see the information you need to appropriately manage the request? | Yes, within the Central FOI Team the Infreemation system is very user friendly, audtiable and timelines of cases are clearly visible. An email is sent to the assigned responding Officer with a full copy of the request.
| Does the system make it clear when a request is a due? | Yes, there is a traffic light system in place and this is very clear.
| When requests are outside the statutory timeframe, are they flagged, either automatically or in regular reports available to the people involved in handling requests? | Yes, they are flagged on the system and captured in the weekly reports sent to the wider organisation. Automatic daily-chasers continue to be sent to the individuals when the request becomes overdue.
| When you have decided that you need to redact information, is the actual process of redacting it straightforward? | Yes, Adobe Acrobat is the system software used to redact cases and bespoke training is provided to services.
| Do you have issues with large file sizes when you need to gather large bundles for disclosure, or redact large documents? | No.
| Are there any other sticking points caused by the systems you use to handle requests which frequently add time or complexity to the handling of requests? | No.
Organisational | Does the organisation as a whole understand the importance of information rights legislation? | On-going training is provided to the whole organisation so as to continually improve the understanding of information rights. The Central Information Management Team also provides bespoke training to services and regularly circulates internal articles on the topic.
| Are staff appropriately trained in recognising and handling information requests (including systems you use and the procedures you follow)? | The organisation receives good training on individual systems. Staff are also provided with practical guides on processing FOIs and particularly applying exemptions.
| Is refresher training available for those who may need it? | Yes, all staff are required to complete yearly refresher training.
| Is it quick and easy to get responses from elsewhere in the organisation when you need to? | Improvements are being made in this area. We have identified key-contacts within the organisation who help close requests within timescales.
| Does oversight of request responses by senior staff, or other people in the organisation, introduce delay? | Director approval process and Press sign-off was not fully defined, so could at times could slow the process down. We have recently reviewed this process and allowed 5 working days within the FOI timeframes for this.
| Is that delay justifiable – for example, has that oversight identified opportunities to disclose further information or avoided any inappropriate disclosures of information? | Some signoff delays are necessary to protect the business functions of the Council. However, we try to minimise these delays as much as possible and to build the required time into the standard allowed FOI response timeframes.
| Are you regularly reporting information rights compliance statistics to senior management boards? Are you flagging and considering the risks posed by falling compliance? | Yes, weekly and monthly reports are sent to the Central Management Team and Directorate Management Teams. We also discuss issues risks at a monthly internal control board.

## Action Plan
We have designed this template after reviewing numerous action plans sent to us by organisations working to recover from compliance issues. You can tailor the structure to help your organisation. We have populated this template with some example actions. They may not reflect your specific needs but combined with your answers to the key questions, they should give you good starting points to identify actions you can take now to improve your compliance with the statutory timeframes.
| Who is responsible for this plan? |  | Chris Dyson - LBC Data Protection Officer
| What is the main objective? |  | Clear all outstanding overdue FOIs and ensure the process hits timescales
| What is the timescale? |  | Within 6 months, before the start of 2024
| Action What steps do you need to take? | Action: | Impact Why do you need to take this action? | Priority High/med/low | Owner Who is responsible for this action? | Start When will you start? | End When are you aiming to finish work on this action? | Review to be updated regularly - what have you done so far, and what is causing delay? | Completed When did you complete the action?
Procedural - How you handle the requests you receive | Example: Set up weekly clinics for team members to discuss requests | Twice weekly meetings within the central team to discuss due cases and any escalations. Weekly reports sent to wider organisation identifying overdue cases and performance. Fortnightly clinics at Directorate Management Team (DMT) meetings. | Establish and share best practice to handle requests more efficiently | High | Information Team Manager | 2023-07-14 | On-going | As of 14/07/2023 Information Management (IM) are attending DMTs on a monthly basis to review all overdue cases and identify colleagues to assist in closure - Resources DMT resulted in the closure of 24 cases. Exemptions and further training has been offered to all FOI contacts in the wider organisation to assist in this process. | Completed
| Example: Explore whether it is possible to assign further staff to request handling in the short term, to work through the backlog | A new fulltime FOI & SAR Officer and a new admin resource to be brought in for six months, until a full service and resource review is completed. Directorates have identified single point of contact within in each team of a sufficiently senior level and are identifying additional capacity to assist in the backlog closure. | Increased resources will ensure better future resilience and help will improve compliance | High | Data Protection Officer | 2023-07-21 | 2023-09-01 | Approval received - currently recruiting. Directorates identifying staff to assist with completion of backlog
| Example: Introduce a triage system to identify straightforward, complex and/or voluminous requests | Additional sufficiently skilled admin staff being brought in to triage cases which can be closed straight away and cases which require to be escalated immediately. This will help FOI Officers and enable the focus to be on responding to requests. | Understanding the nature of your caseload allows officers to focus resources on complex cases as soon as possible. Identifying straightforward requests means a wider pool of staff can deal with those cases that are less complex. | High | Information Team Manager | 2023-08-01 | 2023-09-01 | Information Team Manager is currently interviewing for an admin assistant and will setup this process
Technical - The tools and resources available to you | Example: Identify technology that need to be replaced or reconsidered because they regularly introduce delay | New system purchased for processing FOI/SAR 'Infreemation' and operational from September 22. New reporting functionality added and regular updates. | Using appropriate technology to handle large amounts of documents and redact information will save time | Medium | Head of Corporate Technology | 2022-09-01 | 2022-09-01 | New system purchased in Sept 22 to process all FOI/SAR. The system is regularly reviewed to ensure it remains fit for purpose and continues to meet Council's needs. Since deployment, these reviews have resulted in new reporting for Internal Reviews and update of key directorate contacts. New templates and automated daily chase emails. | Completed
| Example: Ensure staff handling requests correctly store correspondence about each request in a way which allows you to find it and read it easily | Additional staff training is being provided to key nominated staff on the FOI processing systems which means consistency of storage will be achieved | It will be easier and quicker to share, collaborate on, and review requests | Medium | Information Team Manager / Systems Support | 2023-07-24 | 2023-09-01 | Key contacts within directorates have been updated and ongoing and regular training will be given as required.
| Ensure Officers have the tools needed to make the process as efficient as possible | Additional purchases of Adobe Professional software licenses for key directorate Officers supporting the FOI process for redaction | To ensure that the central FOI team are able to focus on complex cases and giving advice. Allowing services to redact prior to sharing for peer review | Medium | Information Team Manager / Heads of Service | 2023-07-17 | 2023-08-01 | This has been agreed, licenses and software installed. Training to be given throughout August to teams.
| Ensure easy access to historic FOI data sets | Ensure that the external website is user-friendly so that members of the public can easily find, or be pointed to, data released in historic FOI requests, and the organisations FOI performance and improvement plan. | This will improve the efficiency of FOI Officers time and reduce the number of repeated requests for the same information. | High | Information Team Manager | 2023-07-03 | 2023-09-01 | Information Team Manager has been working with colleagues in the Website Team to make the FOI pages more user-friendly.
| Example: Consider what reporting capabilities are available to you, and whether they are currently providing you with timely and relevant information | Weekly management reports have been introduced and circulated to the wider organisation including CEO, Corporate Directors and Directors. Back-log requests are shared with Corporate Directors to be discussed at weekly departmental management meetings. | Understanding performance, what is in the queue, and what is closed within the time limit. This will allow resources to meet timescales and key performance measures. | High | Information Team Manager / Corporate Directors | 2022-07-03 | On-going | Information Team Manager and DPO attending directorate management meeting as requested. | Completed
Organisational - How your organisation as a whole can support this plan | Example: Ensure all staff are appropriately trained - use ICO training materials if necessary | New Freedom of Information training created to be delivered to all FOI contacts. Training will be provided on applying exemptions to key staff via legal team and written guides will be produced to support the training. | Time taken to recognise and refer requests, and to respond to internal consultations will be improved | High | Information Team Manager / Information Governance Legal Specialist | 2023-08-01 | 2023-09-01 | Information Team Manager sharing quick guides to key staff. Legal Specialist arranging training for first week in August with key Directors
| Example: Communicate to senior staff the risks posed by falling compliance rates, and blockers to achieving compliance | To improve internal governance, an Information Management Control (IMC) Board has been set up, chaired by the Council's Monitoring Officer. The performance of the FOI function will be reported here routinely. In addition the information will be reported to the Corporate Management Team on a monthly basis. The FOI Improvement Action Plan progress will be reported to the IMC Board and a fortnightly meeting with the Monitoring Officer and the Assistant Chief Executive will take place, until the improvement actions are embedded and a sustainable service is being provided. | An appreciation of the implications of failing to comply, and the causes of non-compliance, can help to focus senior staff on adequately resourcing request handling. Provide stronger insight to FOI performance across the organisation and ensure the organisations maturity is increased. | High | Chief Digital Officer | 2023-07-01 | On Going | Internal briefing note send out by the Chief Digital Officer and over-due cases send to Corporate Directors. On-going fortnightly review with the Monitoring Officer and Assistant Chief Executive. | Completed
| Example: Set and communicate clear expectations for responses from colleagues across the organisation when they are involved in information request handling | Review of the Press Office process and Director sign-off | Remove delays from the handling process | High | Data Protection Officer / Information Team Manager | 2023-07-01 | 2023-08-01 | We are correctly reviewing the process and building in signoff time. Staff will be updated