## Climate Action Plan (hidden)
Getting the Groundwork Right
S.No | Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments | Bronze
1 | Establish oversight and accountability | [8 empty] | 24-25 | 25-26 | 26-27
1.1 | Have a lead Councillor take on the responsibility of overseeing implementation of recommendations | LBC Officers (LBCO), Cabinet Member (CM) | Cabinet Member | Enabling activity | Low | Ongoing | Zero cost | Cllr Scott Roche to be lead Councillor for the Climate Action plan
1.2 | Establish governance board for Carbon Neutrality to drive the implementation of the CNAP | LBCO, CMT, CM | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low
1.3 | Publish Croydon Council's Scope 1 and Scope 2 emissions | LBC Officers (LBCO), CNT | CNT(Carbon Neutral Team) | Enabling activity | Low | Annually | Low | The Council 's emissions will be reported through the Annual Report
1.4 | Inclusion of Scope 3 emissions | LBC Officers (LBCO), Carbon Neutral Team (CNT) | CNT | Enabling activity | Low | Annually | Low | The counci will begin to include Scope 3 emissions starting with its supply chain and further expand to other aspects of Scope 3 | This will be reviewed with availability of internal funding to pursue this. | 25000
1.5 | Baseline the existing Scope 3 carbon emissions ( from supplier base) | LBCO, | Procurement Team | Enabling activity | Low | Annually | Low
1.6 | The Croydon Local Government Pension Fund, to the extent that it is in accordance with adopted Investment Policy, has committed over time to working with investments that have a strong environmental, social and governance policy. Disclosure to be done as per Climate Change Disclosures that are mandated | LBCO | CMT | Medium | High | Ongoing | Low | The adopted Investment Strategy, the Fund aims, over time, to invest in assets that positively address environmental, social and governance policy issues- Disclosure to be done as per Climate Change Disclosures that are madated
1.7 | Integrate climate action commitments,including net zero targets, adaptation, and mitigation strategies across all Council strategies and policies by embedding them into the existing governance processes, frameworks and partnership Boards | LBC Officers (LBCO), Carbon Neutral Team (CNT) | CMT & CNT | Enabling activity | Medium | Ongoing | Low
1.8 | Define, seek approval and then establish the external forum/ alliance of partners made up of stakeholder representatives from diverse groups across the borough to engage on progress being made towards carbon neutrality | LBCO, R, CO, LB, CM and AO, EP | CNT | Enabling activity | Medium | Aug 2025 | Low | Scope and purpose of the forum will be set out and reported to members for further consideration and approval.
1.9 | Establish net zero commitments in procurement strategy. Review procurement policies, guidance documents and templates to establish a comprehensive approach to Net Zero priorities through the procurement and management of Council contracts. | LBCO, | Procurement Team | Enabling activity | Low | Ongoing | Low
2 | Lead by example
2.1 | Implement a transformative organizational cultural shift that emphasizes carbon literacy and sustainability as core value. Encourage staff and councillors undertake climate education | LBCO, CMT, CM | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low | Establish a sustainabilitiy network and improving climate literacy in the Council
2.2 | Publish an annual review of the Carbon Neutral Action Plan | LBCO, CMT, CNT | CNT | Enabling activity | Low | Anually | Low
2.4 | Encourage locally sourced and plant-based food alternatives within the Council and at its events. | LBCO | CNT | Enabling activity | Low | Ongoing | Low
Contribute to a broader ongoing knowledge exchange
2.5 | Quarterly newsletter from Croydon Council | LBC Officers (LBCO), Carbon Neutral Team (CNT) | Comms Team and CNT | Enabling activity | Low | Ongoing | Low
2.6 | Ensure ongoing engagement with other councils/ Greater London Authority (GLA) to inform best practice and assess opportunities for collaboration. | LBC Officers (LBCO), Carbon Neutral Team (CNT) | CNT | Enabling activity | Low | Ongoing | Low
Tackle climate change adaptation risks across the borough
2.7 | Tackle climate change adaptation risks across the borough by initiating a climate risk assesment across the borough | LBCO, External Expertise (EE) | CNT | Enabling activity | High | Sep 2025 | Medium | To examine how risks will evolve in future and distinguish actions within the council’s direct control and actions that require national support. Financial commitment required |  | 60000
3 | Embed carbon reduction and climate adaptation in all the activities and strategies of the Council and its key partners
3.1 | Conduct a review of council policies and strategies to ensure that both climate adaptation and emissions mitigation are embedded where appropriate. Develop a plan of action with a clear timeline to embed these actions across all relevant policies and strategies to the extent that this is permissible by law. | LBCO, CMT, CM | CMT/Governance Body | Enabling activity | Low | Augch 2026 | Low | Many policies and strategies of the Council are governed by statutory parameters and statutory guidance and the Council must adhere to those in formulating any suggestions in this regard or in undertaking any reviews of such policies or strategies. The Council also has a policy framework of strategies, plans and policies which may only be revised or updated by Full Council.
3.1 | Conduct a review of processes guiding the Council’s involvement with external partners as part of the journey towards climate action | LBCO, AO, LB | CNT | Enabling activity | Low | Dec 2025 | Medium
3.1 | Dim existing street lighting by 50% | LBCO, | Street Lighting | Medium | Low | Ongoing | Low
3.1 | Secure Warm Homes Local Delivery Grants | LBCO | Energy Team | Enabling activity | Medium | Aug 2026 | Medium | The council has re-designed it's utility management service by outsourcing bill validation and management to an external provider. The utility bill data is managed in web based database. A set of standard reports are being agreed with the new provider. An agreed set of carbon reporting will be implemented by March 25
3.1 | Enable schools to develop a carbon reduction plan in and have dedicated sustainability leads | LBCO, CNT, EP | CNT | Enabling activity | Low | Ongoing | Low | To work with Lets Go Zero and enable Croydon schools towards carbon reduction
3.1 | Work with highway contractors to reduce the carbon footprint of their operations whilst undertaking work on our behalf | LBCO, EP | Highways & Parking | Enabling activity | Low | Ongoing | Low |  |  | 25000 | 25000
3.1 | Investigate, consider and embed new ways of working that help reduce the carbon output when designing and commissioning construction works for roads and highways maintenance operations | LBCO | Highways & Parking | Enabling activity | Low | Ongoing | Low |  |  | 25000 | 25000
Driving a Green Economic Recovery
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote green jobs and skills
| LBC officers with London Southbank University to support businesses in carbon reduction, energy efficiency commercial building retrofit and circularity | LBCO, London Southbank University | Economic Development Team | Enabling activity | Low | Ongoing | Low | The LSBU Innovation centre will focus on research and development into technology for energy conservation and retrofitting, as well as addressing issues of inclusivity within these jobs and the industry.
| LBC officer run an employment and skills forum with the aim of understanding and reacting to skill gaps and employer needs. | LBCO, Education Providers (EP) | Economic Development Team | Enabling activity | Low | Quarterly events | Low | LBC officers exploring expanding to include an employer skills forum. Working with SLP on bridging the gap.
Strengthen the local and foundational economy
| Establish a green business network and provide engagement and support for business communities to promote initiatives towards carbon reduction and embracing circularity | LBC0,LB | Economic Development Team/CNT | Enabling activity | Low | Ongoing | Low
| Council actively promotes the adoption of toolkits to local SMEs to support them to reduce their carbon footprint. | LBCO, LB | Economic Development Team | Enabling activity | Medium | Ongoing | Medium | Toolkits and other public and business resources will continue to be promoted through LBC communications campaign.
Strengthen the circular economy and recycling rates
| Croydon’s first Community Reuse Shop opened in November 2021. It sells refurbished goods that have been saved from disposal by the Household Reuse and Recycling Centre teams across the South London Waste Partnership (SLWP). Promote reuse shop and look for futher opportunities to set up resuse shops | LBCO, SLWP, R | Waste & Recycling Team | Low | Medium | Annually | Low | Publish metrics on waste resused at the Addington resuse shop; Scope out and work on setting up a reuse shop at Factory Lane
| Reduction of food waste to landfill | LBCO, SLWP, R | Waste & Recycling Team | Low | Medium | Annually | Low | Reduce food waste through ongoing campaigns
| Croydon Council is part of the South London Waste Partnership. To achieve recycling target of 45% | LBCO, SLWP, R | Waste & Recycling Team | Low | High | Annually | Medium | To improve recycling rates as per the Waste Reduction and Recycling Plan
| Introduce greater recycling facilites across our estates | CMT, LBCO, CO | HRA Team | Low | Medium | Aug 2026 | Medium |  |  | 300000
Greening our Neighbourhoods
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Increase renewable energy production
| Council officers to engage with London Council working group exploring the feasibility of developing a power purchasing arrangement to improve the renewable mix in PPA | LBCO, London Council Working Group | Energy Team | Enabling activity | High | Ongoing | High | Council's current and 2024 electricity contracts compatible with renewable PPA which can be entered into separately from retail supplier. 'Pilot' PPA contract proceeding with group of London Boroughs | Council to review experience of pilot boroughs. Any PPA will require at least 10 yr term, so key internal decision will be financial risk
Develop a pipeline of retrofit projects
| To shortlist 100 properties to decarbonise using the Social Housing Decarbonisation Fund | CMT, LBCO, CO | HRA Team | High | High | Aug 2025 | High |  |  | 1000000
| Croydon Healthy Homes (CHH) to tackle fuel poverty by improving the energy efficiency of homes and reduce residents’ fuel bills. | LBCO, R | Energy Team | Medium | Low | Ongoing | Medium | Carbon savings dependent on availability of government grant schemes. CO2 savings to date mostly secured from LAD scheme (now closed). The fuel poverty advice and support to apply when schemes are available will continue
| Conduct a detailed housing stock retrofit needs analysis via consultants | LBCO, R | HRA | Enabling activity | Low | Aug 2025 | Low | Yearly Review of progress |  | 200000
Greening our Neighbourhoods
| Create a Local Area Energy Plan | LBCO, CMT, AO, LB | CNT | Enabling activity | Medium | Dec 2025 | Medium |  |  | 150000
| Whole building decarbonisation plans for council maintained schools | LBCO, EP | Capital Delivery | Enabling activity | Medium | Dec 2025 | Medium |  |  | 92500 | 92500
| Include the use of warm mix asphalt on 10 to 30% of our resurfacing and reconstruction schemes to make carbon savings | LBCO | Highways & Parking | Low | Low | Ongoing | Low |  |  | 83000 | 83000 | 83000
| Enhancements to road to extend life span rather than replacement of road | LBCO | Highways & Parking | Medium | Low | Ongoing | Low |  |  |  | 60000 | 60000
Develop local retrofit delivery capacity
| Support creation of a resource for private retrofit advice. | LBCO, SLP | CNT | Enabling activity | Low | Dec 2027 | Low | South London Partnership exploring opportunity to create this resource.
Croydon Local Plan
| Implement Croydon’s Local Plan and London Plan policies, inclusive of new policies forthcoming as part of the ongoing Local Plan Review, which include carbon neutral realted policies. | LBCO, TfL, R, AO, DfT | Planning Team | High | Ongoing | Medium | LBCO capacity, external organisation input | LBCO capacity, external organisation input
| Council officers are undertaking Croydon Local Plan Review and adoption anticipated by Dec'25 | LBCO, R | Planning Team | Medium | Medium | Dec 2025 | Medium
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote public transport and active travel to become the natural first choice
| Design and deliver bus priority schemes | LBC, TfL | Strategic Transport/Tom Sweeney | Low | Medium | Mar 2026 | Medium | Addington Village interchange bus priority scheme progressing. On site early 2025. Further schemes to be agreed with TfL.
| Deliver cycle training for adults and children | LBC, TfL | Strategic Transport/Tom Sweeney | Low | Low | Aug 2025 | Low | On-going delivery. Reprocurement of cycle training provider is required going forward.
| Install at least 10 cycle parking hangars | LBC, TfL | Strategic Transport/Tom Sweeney/ | Low | Medium | Aug 2025 | Low | On-going delivery. Reprocurement of cycle parking provider is required going forward.
| Identify medium term improvements for at least two railway stations | LBC, Network Rail, Train Operators | Strategic Transport/Sally Crew | Enabling Activity | Medium | Aug 2025 | Low | Officer appointed and work commenced to look at stations
| LBC to continue to lobby TfL to procure a new tram fleet. | LBC, TfL | Strategic Transport/Sally Crew | Enabling Activity | High | Aug 2025 | Low | Prequalification question stage has been completed and the ITT expected to be published imminently
| Commence delivery of Reconnected Croydon schemes | LBC, TfL, MHCLG, GLA | Strategic Transport/Stephen Wojcik | High | High | Aug 2025 | High | First schemes scheduled to be on site early 2025.
| Design and consult on next tranche of Healthy School Streets | LBC, TfL | Strategic Transport/Tom Sweeney | Medium | Medium | Aug 2025 | Medium | Engagement and traffic order making underway. Delivery to commence early 2025.
| Develop approach to guide future tranches of Healthy School Streets | LBC | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | Aug 2025 | Medium | Underway and will be completed in 2024.
| Complete delivery of TfL LIP funded highway safety and walking and cycling schemes | LBC, TfL | Strategic Transport/Tom Sweeney | Medium | Medium | Aug 2025 | Medium | On-going delivery of schemes as part of annual settlement.
| Develop and agree 3 Year plan for TfL Local Impementation Plan funding | LBC, TfL | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | Aug 2025 | Low | Underway and will be completed in 2024.
Greening our Neighbourhoods
Provide the infrastructure to enable the use of electric cars and reducing tranport emissions
| Install at least 25 additional slow and fast electric vehicle charging sockets | LBC | Strategic Transport/Kieran Fitsall | Low | Medium | Aug 2025 | Low | Approval of interim EVCP network expansion plan being progressed.
| Secure LEVI funding and procure supplier | LBC, Other Local Authorities, London Councils, OZEV | Strategic Transport/Kieran Fitsall | Enabling Activity | Medium | Aug 2025 | Medium | Partnership application has been submitted
| Introduce measures aimed at a reduction in car usage, which may include park-and-ride schemes, car clubs. | LBCO, TfL, DfT, R, LB, LC | Highways & Parking | Medium | Medium | Ongoing | Medium |  |  |  | 500000 | 500000
| Create and publish Fleet Strategy for the council | LBCO | Fleet Team | Enabling Activity | Low | Ongoing | Low | Of the 109 vehicles owned by the Council, 54 are not ULEZ compliant; Procurement to be undertaken to replace them to be ULEZ compliant
| Electrify Stubbs Mead Depot and provide EV infrastructure | LBCO | Fleet Team | Medium | Medium | Aug 2027 | Medium |  |  |  | 40000
| Get all fleet vehciles ULEZ compliant and introduce EVs in Fleet operations | LBCO | Fleet Team | Medium | Medium | Dec 2025 | Medium
| Green and blue infrastructure | [6 empty] | Draft for consultation published in 2024; likely to be adopted in 2025.
| The Council Trees and Woodlands Team obtained £411k funding which will result in 491 trees being planted and maintaned for a 3 year establishmeant period. Approximately 40 trees have been spnsored through the councils Sporsorship scheme in partnership with Trees For Streets. Plant additonal 50 trees to the existing programme | LBCO, R, Local Councillors (LC) | Trees and Woodlands Team | Low | Low | Annually | Medium
| Introduce SUDS on Highways | LBCO | Highways & Parking | Low | Low | Ongoing | Medium
| Increase the area of naturalised grass and reduce maintenance to improve wild areas and carbon storage | LBCO | Parks and Green Spaces Team | Low | Low | June 2025 | Low | Dependent on external funding success.
| Implementing 25K sq m of flower meadow | LBCO | Parks and Green Spaces Team | Medium | Medium | Aug 2027 | Low |  |  | 50000 | 2500 | 2500
| Replace end of life hand tools for grounds maintenance from petrol to electric | LBCO | Parks and Green Spaces Team | Low | Low | Aug 2028 | Low |  |  | 2200 | 2200 | 2200
| Flood alleviation works and accompanied mitigation and adaptive measures to be continued including SUDs at Park Hill. Creation of a wetland at Ashburton Park with SUD systems to include sensory garden and meadow/naturalised areas. | LBCO, LC, LB, R | Parks and Green Spaces Team | Low | Medium | June 2025 | Medium
| Establish ambitious, collaborative tree planting targets. Inclusive of Schools Tree Planting Drive, the Trees for Streets programme and other initiatives e.g. UKSPF / London Tree Ring | LBCO, EP, R, CO, AO | Trees and Woodlands Team | Low | Low | Ongoing | Medium
| The existing Biodiversity Action Plan will be updated in time with the green infrastructure strategy. | LBCO, R, CO, LC, CM | Trees and Woodlands Team | Low | Low | June 2026 | Low
Getting People and Businesses Involved
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote action at scale
| Create a network of schools’ and enable schools to prepare carbon reduction plans | LBCO, EP | CNT | Medium | Medium | Ongoing | Medium | LBCO capacity and external organisation input.
| Explore funding schemes to implement and coordinate carbon reduction in schools. Enable availability of data to determine pathways to carbon reduction and applying for funding when they are available | LBCO, EP | Capital Delivery | Enabling activity | Medium | Ongoing | Medium
| Promotion of Trees for Cities | LBCO, EP | Trees and Woodlands Team | Enabling activity | Low | Ongoing | Low | Such as, provision of affordable public transport for economically disadvantaged; LBCO Capacity
Achieving the Scale of Change
| Actions | Key Stakeholders | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement
Lobbying the GLA, TfL, and national government
| Lobbying focus on provision of appropriate long-term funding to support delivery of climate adaptation and carbon neutral target ambitions. | LBCO, CMT, CM, AO | Politicans | Enabling activity | Medium | Ongoing | Medium
| Lobbying to ensure forthcoming regulation and funding opportunities support the ambition for a fair, green recovery. | LBCO, CMT, CM, AO | Politicans | Enabling activity | Medium | Ongoing | Medium

## New Plan Example (hidden)
Getting the Groundwork Right
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Establish oversight and accountability
Have a lead Councillor take on the responsibility of overseeing implementation of recommendations | Cabinet Member | Enabling activity | Low | Ongoing | Zero cost | Cllr Scott Roche to be lead Councillor for the Climate Action plan
Establish governance board for Carbon Neutrality to drive the implementation of the CNAP | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low
Publish Croydon Council's Scope 1 and Scope 2 emissions | CNT(Carbon Neutral Team) | Enabling activity | Low | Annually | Low | The Council 's emissions will be reported through the Annual Report
Inclusion of Scope 3 emissions | CNT | Enabling activity | Low | Annually | Low | The counci will begin to include Scope 3 emissions starting with its supply chain and further expand to other aspects of Scope 3 | This will be reviewed with availability of internal funding to pursue this.
Baseline the existing Scope 3 carbon emissions ( from supplier base) | Procurement Team | Enabling activity | Low | Annually | Low
The Croydon Local Government Pension Fund, to the extent that it is in accordance with adopted Investment Policy, has committed over time to working with investments that have a strong environmental, social and governance policy. Disclosure to be done as per Climate Change Disclosures that are mandated | CMT | Medium | High | Ongoing | Low | The adopted Investment Strategy, the Fund aims, over time, to invest in assets that positively address environmental, social and governance policy issues- Disclosure to be done as per Climate Change Disclosures that are madated
Integrate climate action commitments,including net zero targets, adaptation, and mitigation strategies across all Council strategies and policies by embedding them into the existing governance processes, frameworks and partnership Boards | CMT & CNT | Enabling activity | Medium | Ongoing | Low
Define, seek approval and then establish the external forum/ alliance of partners made up of stakeholder representatives from diverse groups across the borough to engage on progress being made towards carbon neutrality | CNT | Enabling activity | Medium | July 2025 | Low | Scope and purpose of the forum will be set out and reported to members for further consideration and approval.
Establish net zero commitments in procurement strategy. Review procurement policies, guidance documents and templates to establish a comprehensive approach to Net Zero priorities through the procurement and management of Council contracts. | Procurement Team | Enabling activity | Low | March 2025 | Low
Lead by example
Implement a transformative organizational cultural shift that emphasizes carbon literacy and sustainability as core value. Encourage staff and councillors undertake climate education | CMT (Corporate Management Team) | Enabling activity | Low | Ongoing | Low | Establish a sustainabilitiy network and improving climate literacy in the Council
Publish an annual review of the Carbon Neutral Action Plan | CNT | Enabling activity | Low | Anually | Low
Resource staff for Carbon Neutral Team | CMT | Enabling activity | Low | Ongoing | Low | Currently, it is a team of two- Carbon Neutral Programme Manager and Carbon Neutral Project Officer
Enhance availability to locally sourced and plant-based food alternatives within the Council and at its events. | CNT | Enabling activity | Low | Ongoing | Low
Contribute to a broader ongoing knowledge exchange
Quarterly newsletter from Croydon Council | Comms Team and CNT | Enabling activity | Low | Ongoing | Low
Ensure ongoing engagement with other councils/ Greater London Authority (GLA) to inform best practice and assess opportunities for collaboration. | CNT | Enabling activity | Low | Ongoing | Low
Tackle climate change adaptation risks across the borough
Tackle climate change adaptation risks across the borough by initiating a climate risk assesment across the borough | CNT | Enabling activity | High | September 2025 | Medium | To examine how risks will evolve in future and distinguish actions within the council’s direct control and actions that require national support. Financial commitment required
Embed carbon reduction and climate adaptation in all the activities and strategies of the Council and its key partners
Conduct a review of council policies and strategies to ensure that both climate adaptation and emissions mitigation are embedded where appropriate. Develop a plan of action with a clear timeline to embed these actions across all relevant policies and strategies to the extent that this is permissible by law. | CMT/Governance Body | Enabling activity | Low | March 2026 | Low | Many policies and strategies of the Council are governed by statutory parameters and statutory guidance and the Council must adhere to those in formulating any suggestions in this regard or in undertaking any reviews of such policies or strategies. The Council also has a policy framework of strategies, plans and policies which may only be revised or updated by Full Council.
Conduct a review of processes guiding the Council’s involvement with external partners as part of the journey towards climate action | CNT | Enabling activity | Low | December 2025 | Medium
Dim existing street lighting by 50% | Street Lighting | Medium | Low | Ongoing | Low
Implement an Energy Management System within the Council | Energy Team | Enabling activity | Medium | March 2025 | Medium | The council has re-designed it's utility management service by outsourcing bill validation and management to an external provider. The utility bill data is managed in web based database. A set of standard reports are being agreed with the new provider. An agreed set of carbon reporting will be implemented by March 25
Enable schools to develop a carbon reduction plan in and have dedicated sustainability leads | CNT | Enabling activity | Low | Ongoing | Low | To work with Lets Go Zero and enable Croydon schools towards carbon reduction
Work with highway contractors to reduce the carbon footprint of their operations whilst undertaking work on our behalf | Highways & Parking | Enabling activity | Low | Ongoing | Low
Investigate, consider and embed new ways of working that help reduce the carbon output when designing and commissioning construction works for roads and highways maintenance operations | Highways & Parking | Enabling activity | Low | Ongoing | Low
Driving a Green Economic Recovery
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote green jobs and skills
LBC officers with London Southbank University to support businesses in carbon reduction, energy efficiency commercial building retrofit and circularity | Economic Development Team | Enabling activity | Low | Ongoing | Low | The LSBU Innovation centre will focus on research and development into technology for energy conservation and retrofitting, as well as addressing issues of inclusivity within these jobs and the industry.
LBC officer run an employment and skills forum with the aim of understanding and reacting to skill gaps and employer needs. | Economic Development Team | Enabling activity | Low | Quarterly events | Low | LBC officers exploring expanding to include an employer skills forum. Working with SLP on bridging the gap.
Create a Local Area Energy Plan | CNT | Enabling activity | Medium | December 2025 | Medium
Strengthen the local and foundational economy
Establish a green business network and provide engagement and support for business communities to promote initiatives towards carbon reduction and embracing circularity | Economic Development Team/CNT | Enabling activity | Low | Ongoing | Low
Council actively promotes the adoption of toolkits to local SMEs to support them to reduce their carbon footprint. | Economic Development Team | Enabling activity | Medium | Ongoing | Low | Toolkits and other public and business resources will continue to be promoted through LBC communications campaign.
Strengthen the circular economy and recycling rates
Croydon’s first Community Reuse Shop opened in November 2021. It sells refurbished goods that have been saved from disposal by the Household Reuse and Recycling Centre teams across the South London Waste Partnership (SLWP). Promote reuse shop and look for futher opportunities to set up resuse shops | Waste & Recycling Team | Low | Medium | Annually | Low | Publish metrics on waste resused at the Addington resuse shop; Scope out and work on setting up a reuse shop at Factory Lane
Reduction of food waste to landfill by 10% | Waste & Recycling Team | Low | Medium | Annually | Low | Reduce food waste through ongoing campaigns
Croydon Council is part of the South London Waste Partnership. To achieve recycling target of 45% | Waste & Recycling Team | Low | High | Annually | Medium | To improve recycling rates as per the Waste Reduction and Recycling Plan
Greening our Neighbourhoods
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Increase renewable energy production
Council officers to engage with London Council working group exploring the feasibility of developing a power purchasing arrangement to improve the renewable mix in PPA | Energy Team | Enabling activity | High | Ongoing | High | Council's current and 2024 electricity contracts compatible with renewable PPA which can be entered into separately from retail supplier. 'Pilot' PPA contract proceeding with group of London Boroughs | Council to review experience of pilot boroughs. Any PPA will require at least 10 yr term, so key internal decision will be financial risk
Develop a pipeline of retrofit projects
To shortlist properties to decarbonise using the Social Housing Decarbonisation Fund once the stock condition survey is complete | HRA Team | Enabling activity | High | March 2025 | High
Croydon Healthy Homes (CHH) to tackle fuel poverty by improving the energy efficiency of homes and reduce residents’ fuel bills. | Energy Team | Medium | Low | Ongoing | Medium | Carbon savings dependent on availability of government grant schemes. CO2 savings to date mostly secured from LAD scheme (now closed). The fuel poverty advice and support to apply when schemes are available will continue
Conduct a detailed housing stock retrofit needs analysis. | HRA | Enabling activity | Low | March 2025 | Low | Yearly Review of progress
Entering a long-term partnership with energy supplier for ECO4 on home improvements for energy efficiency | Energy Team | Medium | Low | March 2026 | Low
Greening our Neighbourhoods
Accelerate decarbonisation of social housing. The Council has 16,000 housing assets and improvements to energy efficiency will be done via retrofitting when appropriate and possible. The detail investment programme will go through different iterations when the stock condition survey completes and we obtain data on other components such as our M&E assets, plant rooms etc. At each iteration, we will detail which homes and buildings are likely to benefit from retrofitting, what elements will be retrofitted and when. | HRA Team | High | High | Ongoing | High |  |  |  | Line 53
Include the use of warm mix asphalt on 10 to 30% of our resurfacing and reconstruction schemes to make carbon savings | Highways & Parking | Low | Low | Ongoing | Low
Enhancements to road to extend life span rather than replacement of road | Highways & Parking | Medium | Low | Ongoing | Low
Develop local retrofit delivery capacity
Support creation of a resource for private retrofit advice. | CNT | Enabling activity | Low | December 2025 | Low | South London Partnership exploring opportunity to create this resource.
Croydon Local Plan
Implement Croydon’s Local Plan and London Plan policies, inclusive of new policies forthcoming as part of the ongoing Local Plan Review, which include carbon neutral realted policies. | Planning Team | High | High | Ongoing | Medium | LBCO capacity, external organisation input
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote public transport and active travel to become the natural first choice
Design and deliver bus priority schemes | Strategic Transport/Tom Sweeney | Low | Medium | March 2026 | Medium | Addington Village interchange bus priority scheme progressing. On site early 2025. Further schemes to be agreed with TfL. |  | Line 61
Deliver cycle training for adults and children | Strategic Transport/Tom Sweeney | Low | Low | March 2025 | Low | On-going delivery. Reprocurement of cycle training provider is required going forward.
Install at least 10 cycle parking hangars | Strategic Transport/Tom Sweeney/ | Low | Medium | March 2025 | Low | On-going delivery. Reprocurement of cycle parking provider is required going forward.
Identify medium term improvements for at least two railway stations | Strategic Transport/Sally Crew | Enabling Activity | Medium | March 2025 | Low | Officer appointed and work commenced to look at stations
TfL commence procurement of new tram fleet | Strategic Transport/Sally Crew | Enabling Activity | High | March 2025 | Low | Prequalification question stage has been completed and the ITT expected to be published imminently
Commence delivery of Reconnected Croydon schemes | Strategic Transport/Stephen Wojcik | High | High | March 2025 | High | First schemes scheduled to be on site early 2025.
Design and consult on next tranche of Healthy School Streets | Strategic Transport/Tom Sweeney | Medium | Medium | March 2025 | Medium | Engagement and traffic order making underway. Delivery to commence early 2025.
Develop approach to guide future tranches of Healthy School Streets | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | March 2025 | Medium | Underway and will be completed in 2024.
Complete delivery of TfL LIP funded highway safety and walking and cycling schemes | Strategic Transport/Tom Sweeney | Medium | Medium | March 2025 | Medium | On-going delivery of schemes as part of annual settlement.
Develop and agree 3 Year plan for TfL Local Impementation Plan funding | Strategic Transport/Tom Sweeney | Enabling Activity | Medium | March 2025 | Low | Underway and will be completed in 2024.
Greening our Neighbourhoods
Create and publish Fleet Strategy for the council | Fleet Team | Enabling Activity | Low | Ongoing | Low
Get DVSA earned recognition scheme or similar for Council's Fleet | Fleet Team | Enabling Activity | Low | Ongoing | Low |  |  | line 73
Introduce measures aimed at a reduction in car usage, which may include park-and-ride schemes, car clubs. | Highways & Parking | Medium | Medium | Ongoing | Medium | Indicators of success would be an overall reduction in car ownership, within the borough. Statutory parameters must be adhered to including in relation to any consultation, notification and publication duties. Lessons learnt must be utilised.
Explore funding schemes to implement and coordinate carbon reduction in schools. Enable availability of data to determine pathways to carbon reduction and applying for funding when they are available | Capital Delivery | Enabling activity | Medium | Ongoing | Medium
Provide the infrastructure to enable the use of electric cars
Install at least 25 additional slow and fast electric vehicle charging sockets | Strategic Transport/Kieran Fitsall | Low | Medium | March 2025 | Low | Approval of interim EVCP network expansion plan being progressed.
Secure LEVI funding and procure supplier | Strategic Transport/Kieran Fitsall | Enabling Activity | Medium | March 2025 | Medium | Partnership application has been submitted
Electrify Stubbs Mead Depot and provide EV infrastructure | Fleet Team | Medium | Medium | March 2027 | Medium
Get all fleet vehciles ULEZ compliant and introduce EVs in Fleet operations | Fleet Team | Medium | Medium | December 2025 | Medium | Of the 109 vehicles owned by the Council, 54 are not ULEZ compliant; Procurement to be undertaken to replace them to be ULEZ compliant
Green and blue infrastructure
The Council Trees and Woodlands Team obtained £411k funding which will result in 491 trees being planted and maintaned for a 3 year establishmeant period. Approximately 40 trees have been spnsored through the councils Sporsorship scheme in partnership with Trees For Streets. Plant additonal 50 trees to the existing programme | Trees and Woodlands Team | Low | Low | Annually | Medium
The council participated in and launched the Trees for Streets initiative, enabling residents to sponsor a street tree in their neighbourhood or park. | Trees and Woodlands Team | Low | Low | Ongoing | Medium
Introduce SUDS on Highways | Highways & Parking | Low | Low | Ongoing | Medium
Increase the area of naturalised grass by 20% and reduce maintenance to improve wild areas and carbon storage | Parks and Green Spaces Team | Low | Low | June 2025 | Low
Council officers are undertaking Croydon Local Plan Review and adoption anticipated by Dec'25 | Planning Team | Medium | Medium | December 2025 | Medium | Draft for consultation published in 2024; likely to be adopted in 2025.
Implementing 25K sq m of flower meadow | Parks and Green Spaces Team | Medium | Medium | March 2027 | Low
Replace end of life hand tools for grounds maintenance from petrol to electric | Parks and Green Spaces Team | Low | Low | March 2028 | Low
Flood alleviation works and accompanied mitigation and adaptive measures to be continued including SUDs at Park Hill. Creation of a wetland at Ashburton Park with SUD systems to include sensory garden and meadow/naturalised areas. | Parks and Green Spaces Team | Low | Medium | June 2025 | Medium
Establish ambitious, collaborative tree planting targets. Inclusive of Schools Tree Planting Drive, the Trees for Streets programme and other initiatives e.g. UKSPF / London Tree Ring | Trees and Woodlands Team | Low | Low | Ongoing | Medium | Dependent on external funding success.
The existing Biodiversity Action Plan will be updated in time with the green infrastructure strategy. | Trees and Woodlands Team | Low | Low | June 2026 | Low | This includes a proposed Biodiversity Action Plan and a full Green Infrastructure Strategy from 2025.
Getting People and Businesses Involved
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Promote action at scale
Create a network of schools’ and enable schools to prepare carbon reduction plans | CNT | Medium | Medium | Ongoing | Medium
Promotion of Trees for Cities | Trees and Woodlands Team | Enabling activity | Low | Ongoing | Low
Achieving the Scale of Change
Actions | Responsible Officer | Carbon Impact | Complexity | Delivery Timescales | Resource Requirement | Status | Comments
Lobbying the GLA, TfL, and national government
Lobbying focus on provision of appropriate long-term funding to support delivery of climate adaptation and carbon neutral target ambitions. | Politicans | Enabling activity | Medium | Ongoing | Medium | LBCO capacity and external organisation input.
Lobbying to ensure forthcoming regulation and funding opportunities support the ambition for a fair, green recovery. | Politicans | Enabling activity | Medium | Ongoing | Medium | Such as, provision of affordable public transport for economically disadvantaged; LBCO Capacity

## Climate Action Work Plan
Detailed Climate Work Plan -2030
Getting the Groundwork Right
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
1 | Establish oversight and accountability
1.1 | Have a lead Councillor take on the responsibility of overseeing implementation of CAP | LBC Officers (LBCO), Cabinet Member (CM) | Ongoing | Cllr Scott Roche to be lead Councillor for the Climate Action plan
1.2 | Establish governance board for Climate Action Plan to drive the implementation of the CAP | LBCO, CMT(Corporate Management Team), CM | Ongoing
1.3 | Publish Croydon Council's Scope 1 and Scope 2 emissions | LBC Officers (LBCO), Carbon Neutral Team | Annually | The Council 's emissions will be reported through the Annual Report
1.4 | Inclusion of Scope 3 emissions | LBC Officers (LBCO), Carbon Neutral Team (Carbon Neutral Team) | Annually
1.5 | Baseline the existing Scope 3 carbon emissions (from supplier base) | LBCO | Annually
1.6 | The Croydon Local Government Pension Fund, to the extent that it is in accordance with adopted Investment Policy, has committed over time to working with investments that have a strong environmental, social and governance policy. | LBCO | Ongoing
1.7 | Integrate climate action commitments, including net zero targets, adaptation, and mitigation strategies across all Council strategies and policies by embedding them into the existing governance processes, frameworks and partnership boards | LBC Officers (LBCO), Carbon Neutral Team (Carbon Neutral Team) | Ongoing
1.8 | Define, seek approval and then establish the external forum/ alliance of partners made up of stakeholder representatives from diverse groups across the borough to engage on progress being made towards carbon neutrality | LBCO, R, CO, LB, CM and AO, EP | 2026-03-01 | Scope and purpose of the forum will be set out and reported to members for further consideration and approval.
1.9 | Establish net zero commitments in procurement strategy. Review procurement policies, guidance documents and templates to establish a comprehensive approach to Net Zero priorities through the procurement and management of Council contracts. | LBCO, | Ongoing
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
2 | Lead by example
2.1 | Implement a transformative organisational cultural shift that emphasizes carbon literacy and sustainability as core value. Encourage staff and councillors undertake climate education. | LBCO, CMT, CM | Ongoing | Council has introduced Climate Fresks among staff and Councillors
2.2 | Publish an annual review of the Carbon Action Plan | LBCO, CMT, Carbon Neutral Team | Annually
2.3 | Enhance locally sourced and plant-based food alternatives within the Council and at its events | LBCO | Ongoing
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
2 | Contribute to a broader ongoing knowledge exchange
2.4 | Issue climate updates in Croydon magazine (Our Croydon) | LBC Officers (LBCO), Carbon Neutral Team (Carbon Neutral Team) | Ongoing
2.5 | Ensure ongoing engagement with other Councils/Greater London Authority (GLA) to inform best practice and assess opportunities for collaboration | LBC Officers (LBCO), Carbon Neutral Team (Carbon Neutral Team) | Ongoing
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
2 | Tackle climate change adaptation risks across the borough
2.6 | Tackle climate change adaptation risks across the borough by initiating a climate risk assessment across the borough | LBCO, External Expertise (EE) | 2026-03-01
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
3 | Embed carbon reduction and climate adaptation in all the activities and strategies of the Council and its key partners
3.1 | Conduct a review of Council policies and strategies to ensure that both climate adaptation and emissions mitigation are embedded where appropriate. Develop a plan of action with a clear timeline to embed these actions across all relevant policies and strategies to the extent that this is permissible by law. | LBCO, CMT, CM | 2026-08-01 | Many policies and strategies of the Council are governed by statutory parameters and statutory guidance and the Council must adhere to those in formulating any suggestions in this regard or in undertaking any reviews of such policies or strategies. The Council also has a policy framework of strategies, plans and policies which may only be revised or updated by Full Council.
3.2 | Conduct a review of processes guiding the Council’s involvement with external partners as part of the journey towards climate action | LBCO, AO, LB | 2026-06-01
3.3 | Replace street lighting lanterns with LED lighting | LBCO, | Ongoing
3.4 | Secure Warm Homes Local Delivery Grants | LBCO | 2026-08-01
3.5 | Enable schools to develop a carbon reduction plan in and have dedicated sustainability leads | LBCO, Carbon Neutral Team, EP | Ongoing | To work with Lets Go Zero and enable Croydon schools towards carbon reduction
Driving a Green Economic Recovery
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
4 | Promote green jobs and skills
4.1 | LBC officers with London Southbank University to support businesses in carbon reduction, energy efficiency commercial building retrofit and circularity | LBCO, London Southbank University | Ongoing
4.2 | LBC officer run an employment and skills forum with the aim of understanding and reacting to skill gaps and employer needs | LBCO, Education Providers (EP) | Quarterly events
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
5 | Strengthen the local and foundational economy
5.1 | Establish a green business network and provide engagement and support for business communities to promote initiatives towards carbon reduction and embracing circularity | LBC0,LB | Ongoing
5.2 | Council actively promotes the adoption of toolkits to local SMEs to support them to reduce their carbon footprint | LBCO, LB | Ongoing
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
6 | Strengthen the circular economy and recycling rates
6.1 | Croydon’s first Community Reuse Shop opened in November 2021. It sells refurbished goods that have been saved from disposal by the Household Reuse and Recycling Centre teams across the South London Waste Partnership (SLWP). Promote reuse shop and look for further opportunities to set up reuse shops | LBCO, SLWP, R | Annually
6.2 | Reduction of food waste to landfill | LBCO, SLWP, R | Annually | Reduce food waste through ongoing campaigns
6.3 | Croydon Council is part of the South London Waste Partnership. To achieve recycling target of 45%. | LBCO, SLWP, R | Annually | To improve recycling rates as per the Waste Reduction and Recycling Plan
6.4 | Introduce greater recycling facilities across our estates | CMT, LBCO, CO | 2026-08-01
Greening our Neighbourhoods
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
7 | Increase renewable energy production
7.1 | Council officers to engage with London Council working group exploring the feasibility of developing a power purchasing arrangement to improve the renewable mix in PPA | LBCO, London Council Working Group | Ongoing | Council's current and 2024 electricity contracts compatible with renewable PPA which can be entered into separately from retail supplier. 'Pilot' PPA contract proceeding with group of London Boroughs.
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
8 | Develop a pipeline of retrofit projects
8.1 | To shortlist 100 properties to decarbonise using the Warm Homes: Social Housing Fund Wave 3 | CMT, LBCO, CO | 2025-12-01
8.2 | Croydon Healthy Homes (CHH) to tackle fuel poverty by improving the energy efficiency of homes and reduce residents’ fuel bills | LBCO, R | Ongoing
8.3 | Conduct a detailed housing stock retrofit needs analysis via consultants | LBCO, R | 2025-12-01 | Yearly Review of progress
Greening our Neighbourhoods
8.4 | Create a Local Area Energy Plan | LBCO, CMT, AO, LB | 2026-06-01
8.5 | Whole building decarbonisation plans for council maintained schools | LBCO, EP | 2026-03-01
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
9 | Develop local retrofit delivery capacity
9.1 | Support creation of a resource for private retrofit advice. | LBCO, SLP | Dec 2025 | Completed - https://www.croydon.gov.uk/environment/sustainable-development/sustainability-croydon-0/energy-home-improvements/household-retrofit-guidance-private-properties | 2025-05-01
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
10 | Croydon Local Plan
10.1 | Implement Croydon’s Local Plan and London Plan policies, inclusive of new policies forthcoming as part of the ongoing Local Plan Review, which include carbon neutral related policies. | LBCO, TfL, R, AO, DfT | Ongoing | LBCO capacity, external organisation input
10.2 | Council officers are undertaking Croydon Local Plan Review and adoption anticipated by Dec '25 | LBCO, R | 2025-12-01
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
11 | Promote public transport and active travel to become the natural first choice
11.1 | Design and deliver bus priority schemes | LBC, TfL | 2026-03-01 | Addington Village interchange bus priority scheme progressing. On site early 2025. Further schemes to be agreed with TfL.
11.2 | Deliver cycle training for adults and children | LBC, TfL | 2025-11-01
11.3 | Install at least 10 cycle parking hangars | LBC, TfL | 2025-11-01
11.4 | Identify medium term improvements for at least two railway stations | LBC, Network Rail, Train Operators | 2025-11-01
11.5 | LBC to continue to lobby TfL to procure a new tram fleet | LBC, TfL | 2025-11-01
11.6 | Commence delivery of Reconnected Croydon schemes | LBC, TfL, MHCLG, GLA | 2025-11-01
11.7 | Design and consult on next tranche of Healthy School Streets | LBC, TfL | 2025-11-01
11.8 | Develop approach to guide future tranches of Healthy School Streets | LBC | 2025-11-01
11.9 | Complete delivery of TfL LIP funded highway safety and walking and cycling schemes | LBC, TfL | 2025-11-01
11.91 | Develop and agree 3 Year plan for TfL Local Implementation Plan funding | LBC, TfL | 2025-11-01
12.4 | Create and publish Fleet Strategy for the Council | LBCO | 2025-11-01
12.5 | Electrify Stubbs Mead Depot and provide EV infrastructure | LBCO | 2027-08-01
12.6 | Get all fleet vehicles ULEZ compliant and introduce EVs in Fleet operations | LBCO | 2025-12-01
12.7 | Introduce measures aimed at a reduction in car usage, which may include car clubs | LBCO | 2027-12-01
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
13 | Green and blue infrastructure
13.1 | The Council Trees and Woodlands Team obtained £411k funding which will result in 491 trees being planted and maintained for a 3 year establishment period. Approximately 40 trees have been sponsored through the councils Sponsorship scheme in partnership with Trees For Streets. Plant additional 50 trees to the existing programme. | LBCO, R, Local Councillors (LC) | Annually
13.2 | Introduce SUDS on Highways | LBCO | Ongoing
13.3 | Increase the area of naturalised grass and reduce maintenance to improve wild areas and carbon storage | LBCO | 2026-03-01 | Dependent on external funding success.
13.4 | Implementing 25K sq. m of flower meadow | LBCO | Aug 2027
13.5 | Replace end of life hand tools for grounds maintenance from petrol to electric | LBCO | Aug 2028
13.6 | Flood alleviation works and accompanied mitigation and adaptive measures to be continued including SUDs at Park Hill. Creation of a wetland at Ashburton Park with SUD systems to include sensory garden and meadow/naturalised areas. | LBCO, LC, LB, R | 2025-12-01
13.7 | Establish ambitious, collaborative tree planting targets. Inclusive of Schools Tree Planting Drive, the Trees for Streets programme and other initiatives e.g. UKSPF / London Tree Ring | LBCO, EP, R, CO, AO | Ongoing
13.8 | The existing Biodiversity Action Plan will be updated in time with the green infrastructure strategy. | LBCO, R, CO, LC, CM | 2026-06-01
Getting People and Businesses Involved
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
14 | Promote action at scale
14.1 | Create a network of schools’ and enable schools to prepare carbon reduction plans | LBCO, EP | Ongoing | LBCO capacity and external organisation input.
14.2 | Explore funding schemes to implement and coordinate carbon reduction in schools. Enable availability of data to determine pathways to carbon reduction and applying for funding when they are available | LBCO, EP | Ongoing
14.3 | Promotion of Trees for Cities | LBCO, EP | Ongoing
Achieving the Scale of Change
S.No | Actions | Partners | Delivery Timescales | Status / Progress Notes | Date
15 | Lobbying the GLA, TfL, and national government
15.1 | Lobbying focus on provision of appropriate long-term funding to support delivery of climate adaptation and carbon neutral target ambitions. | LBCO, CMT, CM, AO | Ongoing
15.2 | Lobbying to ensure forthcoming regulation and funding opportunities support the ambition for a fair, green recovery. | LBCO, CMT, CM, AO | Ongoing